## Sheet1
User stories for Student Event Calendar
Customer priority (1 highest) | Difficulty rating (5 highest) | User stories | Assigned | Status
1 | 1 | As a visitor, I would like to see current events on the main page. | Carlos | In progress
1 | 4 | As a user, I would like to share events I am attending on my social media. | Carlos | In progress
1 | 5 | As a site moderator, I would like to use 3rd party software to add an event to the calendar. | Sai | In progress
2 | 1 | As a user, I would like to rsvp to an event. | Terrell | In progress
2 | 3 | As a user, I would like to be able search for specific events within the calendar. | Heather | In progress
2 | 2 | As a site moderator, I would like to keep track of event statistics. | Heather | In progress
3 | 2 | As a user, would like to see events organized by category. | Heather | In progress
3 | 1 | As a site moderator, I would like to edit an event on the calendar. | Terrell | Done
3 | 1 | As a site moderator, I would like to delete an event from the calendar. | Terrell | Done
4 | 1 | As a user, I would like to give feedback to events. | Terrell | In progress
4 | 2 | As a site moderator, I would like to be able see who will attend an event. | Carlos | In progress
5 | 3 | As a visitor, I would like to create an account. | Sai | Done
5 | 2 | As a user, I would like to login to my account. | Sai | Done
5 | 2 | As a user, I would like to edit account information. | Sai | Done
5 | 2 | As a user, I would like to logout out of my account. | Sai | Done
5 | 2 | As a user, I would like to be able to retrieve my lost username/password. | Sai | Done
5 | 3 | As a user, I would like to set a preference for which events I am interested in. | Heather | In progress